## Runbook
Runbook sample - Lift&Shift with Azure Migrate
https://docs.microsoft.com/en-us/azure/migrate/
https://docs.microsoft.com/en-us/azure/cloud-adoption-framework/migrate/
# | Prerequisites | Comment | Executed | Additional resources/References
| Review migration types and select most appropriate tools for assessment and migration | Decision based on virtualization platform & version, OS version, access to virtualization hosts, etc. | Once | https://docs.microsoft.com/en-us/azure/migrate/migrate-services-overview#integrated-tools
| Verify Migration limitations and plan Migration strategy accordingly | Assessment of up to 35,000 servers in a single Azure Migrate Project… Verify support matrix for compatibility of virtualization platform and/or physical servers and VMs | Once | https://docs.microsoft.com/en-us/azure/migrate/prepare-for-migration#verify-migration-limitations https://docs.microsoft.com/en-us/azure/migrate/migrate-support-matrix
| Configure and verify source host prerequisites are in place | Varies for Hyper-V, VMware or Physical server / other virtualization platform | Per host/physical server | https://docs.microsoft.com/en-us/azure/migrate/migrate-support-matrix-vmware#vmware-requirements https://docs.microsoft.com/en-us/azure/migrate/migrate-support-matrix-hyper-v#hyper-v-host-requirements https://docs.microsoft.com/en-us/azure/migrate/migrate-support-matrix-physical#physical-server-requirements
| Prepare Azure environment | Varies for Hyper-V, VMware or Physical server / other virtualization platform: - Create an Azure Migrate project - Register resource providers - Create Azure AD apps - Create a Key Vault | Once | https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-vmware#prepare-azure https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-hyper-v#prepare-azure https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical#prepare-azure-for-server-assessment https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical#prepare-azure-for-physical-server-migration
| Prepare VMware, Hyper-V platform and Physical server infra | Includes specific permissions, configurations and installations required at on-prem platform level. Varies for Hyper-V, VMware or Physical server / other virtualization platform Additional tasks might include instalation of agents on Hyper-V hosts or Mobility service on VMs/physical servers, depending of migration type | Per host/physical server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-vmware https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-hyper-v https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#prepare-hyper-v-hosts
| Prepare VMs/physical servers for assessment and migration | Depending on migration type, some changes might be required on VMs/physical servers | Once | https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical#prepare-for-physical-server-assessment https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical#prepare-for-physical-server-migration
| Configure firewall requirements | Enable connectivity between appliances and Azure Enable connectivity between source servers/VMs and appliance | Once | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware#prepare-vms-for-migration https://docs.microsoft.com/en-us/azure/migrate/common-questions-appliance#what-network-connectivity-is-needed https://docs.microsoft.com/en-us/azure/migrate/migrate-replication-appliance#url-access
| Deploy Azure Migrate appliance(s) | Depending on chosen migration type(s), multiple appliances may be required, such as replication appliance | Once | https://docs.microsoft.com/en-us/azure/migrate/how-to-set-up-appliance-vmware https://docs.microsoft.com/en-us/azure/migrate/how-to-set-up-appliance-hyper-v https://docs.microsoft.com/en-us/azure/migrate/how-to-set-up-appliance-physical
| Verify required networking for target environment is deployed in Azure | Consider DNS configuration, internet connectivity, security… | Once | https://docs.microsoft.com/en-us/azure/virtual-network/virtual-networks-overview
| Verify hybrid network connectivity between on-prem and Azure | Using VPN or ExpressRoute | Once | https://docs.microsoft.com/en-us/azure/architecture/reference-architectures/hybrid-networking/
| Network bandwidth planning and routing requirements (if required) | Capacity Planner will help with estimating network bandwidth required for migration | Once | https://docs.microsoft.com/en-us/azure/site-recovery/site-recovery-capacity-planner#run-the-quick-planner
| Setup a dedicated VNET or a subnet (locked down with NSG) under existing VNET for test failover of servers during migration | During migration test failover, temp failover VM should be in an isolated environment to avoid DNS and production application conflicts. | Once
| Set up Log Analytics workspace for dependency visualisation using Service Map (optional) | Decide on using agent-based or agentless dependencies visualizatuon and set up prerequisites | Once | https://docs.microsoft.com/en-us/azure/migrate/how-to-create-group-machine-dependencies https://docs.microsoft.com/en-us/azure/migrate/how-to-create-group-machine-dependencies-agentless
| Deploy Log Analytics gateway if needed (optional) | Deploy when computers cannot directly connect to internet to access Azure Monitor | Once | https://docs.microsoft.com/en-us/azure/azure-monitor/platform/gateway
| Deploy MMA and Dependency agents on each machine | Dependency agents are required when using agent-based dependency visualization | Per server | https://docs.microsoft.com/en-us/azure/azure-monitor/platform/log-analytics-agent#installation-and-configuration https://docs.microsoft.com/en-gb/azure/migrate/concepts-dependency-visualization
# | Assessment Activities | Comment | Executed | Additional resources
| Interview business/app owners, gather requirements and dependencies | It is critical to undersand application requirements, licensing, dependencies that tools can't discover | Per application/ workload
| Identify/document required UAT test after migration | Gather tests that needs to be run after migration to validate app is performing as expected | Per application/ workload
| Verify all VM/server assessment prerequisites are in place | Verify that all steps for chosen assessment type are in place | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-vmware#prepare-for-vmware-vm-assessment https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-hyper-v#prepare-hyper-v-for-assessment https://docs.microsoft.com/en-us/azure/migrate/tutorial-prepare-physical#prepare-for-physical-server-assessment
| Start continuous discovery and gather data over period of time | It is recommended to gather performance and dependecy data over longer period of time to get more accurate results (for example over period of 5 weeks) | Once
| Create assessment in Azure Migrate Project | After data has been gathered over period of time, create assessment with appropriate parameters. If required create multiple groups for assessment. You can create multiple assessment with different parameters. | As required | https://docs.microsoft.com/en-us/azure/migrate/best-practices-assessment https://docs.microsoft.com/en-us/azure/migrate/how-to-create-a-group https://docs.microsoft.com/en-us/azure/migrate/best-practices-assessment https://docs.microsoft.com/en-us/azure/migrate/how-to-modify-assessment
| Assess Azure suitability/compatibility | Establish if VM can be moved to Azure/identify changes required | Per server | https://support.microsoft.com/en-us/help/2721672/microsoft-server-software-support-for-microsoft-azure-virtual-machines https://docs.microsoft.com/en-us/azure/virtual-machines/linux/endorsed-distros
| Identify dependencies | Using tooling and interviews from app owners | Per server | https://docs.microsoft.com/en-us/azure/migrate/how-to-create-group-machine-dependencies-agentless#visualize-dependencies
| Performance monitoring (optional) | In case of specific requirements or complex applications, implement additional performance monitoring to better select VM size and sotrage type in Azure | Per server
| Sizing based on performance requirements (VM Size, Storage configuration/tier) | Adjust sizing recommendations based on interviews with application owners | Per server
| Group machines based on interviews and discovered dependencies | Prepare group of servers/VMs that will be migrated in same batch and assign servers/VMs to groups. Consider utilizing manual grouping based on existing application architecture documentation, tools (CMDB) and application owners interviews | Per workload or migration group | https://docs.microsoft.com/en-us/azure/migrate/how-to-create-a-group
# | Pre-migration Activities | Comment | Executed | Additional resources
| Verify assessment results and dependencies are up to date | Use recent assessment and dependency analysis results | As required
| Submit change requests if required to obtain access and implement requirements |  | As required
| Obtain and verify Access to server with required permissions are in place | In order to complete any installation/reconfiguration required on server/VM | Per server
| Install replication agents (if required) | In case of using Agent-based migration | Per server | https://docs.microsoft.com/en-us/azure/migrate/agent-based-migration-architecture
| In case of existing agent based replication DR resolve conflicts (if required) |  | As required
| Verify required changes before migration | Prepare VM to run in Azure before migration, consider things like connectivity, SSH/RDP access, Hyper-V Integration services, access to Serial Console, Drive letters/device persistance,… | Per server | https://docs.microsoft.com/en-us/azure/migrate/prepare-for-migration
| Pre-migration health check (OS, Apps, DBs) | Verify health of server/VM and its workloads before migration | Per server
| Initiate replication | Initiate server replication to Azure | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware#replicate-vms https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#replicate-hyper-v-vms https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-physical-virtual-machines#replicate-machines
| Verify replication state | Track and monitor status of replication | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware#track-and-monitor https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#track-and-monitor https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-physical-virtual-machines#track-and-monitor
| Initiate test failover | It is strongly recommended to perform test failover to verify VM boots in Azure and loads as expected. Note that might be challenging to verify application health if using isolated test environments | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware-agent#run-a-test-migration https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#run-a-test-migration https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-physical-virtual-machines#run-a-test-migration
| Verify success of test failover and state of test replica |  | Per server
| Assess and document DNS configuration/records for server/VM | To be able to apply any chages to DNS if required after migration | Per server
| Assess network requirements for server/VM | Discover and document network requirements for VM, such as: - Firewall networking rules - Load balancing requirements | Per server
| Change Netowrk Firewall/NSG configuration on target environment | Configure any required network changes to that migrated server/VM requires in target environment | Per server
# | Migration Activities | Comment | Executed | Additional resources
| Notify owners on migration/get approvals | Notify and get approvals for migration from application owners | Per server
| Perform migration/failover | Initate Migration from Azure Migrate project | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware#migrate-vms https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#migrate-vms https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-physical-virtual-machines#migrate-vms
| Verify success of migration | Track migration and verify success in Azure Migrate project | Per server
| Test network connectivity | Validate that all required connectivity is in place/fix issues if needed | Per server
| DNS changes | Implement any required DNS changes | Per server
| Update Active Directory objects (if requred) | Consider changes to computer object OU… | Per server
| Azure Load Balancer configuration (if required) |  | Per server
| Update application settings | Update any application configuration such as connection strings if required | Per server
| Verify state of Applications/Services | Verify OS and applications running in VM are running healthy | Per server
| UAT tests | Perform UAT tests documented in assessment stage | Per server
| Verify Azure agent is deployed | VMs require Azure agent installed for full Azure integration | Per server | https://docs.microsoft.com/en-us/azure/virtual-machines/extensions/agent-windows https://docs.microsoft.com/en-us/azure/virtual-machines/extensions/agent-linux
| Configure monitoring | Configure/verify monitoring with selected tool | Per server | https://docs.microsoft.com/en-us/azure/virtual-machines/windows/monitor
| Configure Antimalware | Configure/verify VM protection with selected tool | Per server | https://docs.microsoft.com/en-us/azure/virtual-machines/windows/security-policy#antimalware
| Enable backup | Enable backup of VM with selected tool | Per server | https://docs.microsoft.com/en-us/azure/backup/quick-backup-vm-portal
| Enable patching | Enable update management with selected tool | Per server | https://docs.microsoft.com/en-us/azure/automation/automation-update-management
| Complete migration/failback if required |  | Per server | https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-vmware#complete-the-migration https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-hyper-v#complete-the-migration https://docs.microsoft.com/en-us/azure/migrate/tutorial-migrate-physical-virtual-machines#complete-the-migration
# | Post-migration Activities | Comment | Executed | Additional resources
| Update tagging/naming | Add/update any Tags in Azure |  | https://docs.microsoft.com/en-us/azure/virtual-machines/windows/tag
| Update CMDB | Update CMDB with required changes
| Signoff | Signoff on completed server/VM migration
| Decommission | Decomission any on-prem systems thet were required (monitoring, backup…)
Note on D3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add column if done once/per group/per workload...
Note on D8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Need some clarification on # and type of appliances
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Firewalls, network rules - discover network requirements, load balancing requirements... Groups - define batches (Dev first...)
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Lack of documentation on how to define migration groups (use CMDB - if there are groups)
Note on C64: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add to migration - to be done before cutover!

## OS Versions
O